## Sheet1
WBS ID | Task | Deliverable | Owner | Start Date | Status
1.1 | Research gold price data sources | Data sources document | MOHAMMAD NASSAR | 13/11/2025 | DONE
1.2 | Collect historical gold price data | Raw dataset file | AMIR. SHAT | 24/11/2025 | Not Started
1.3 | Clean and preprocess data | Cleaned dataset | HUSAM MOHAMED | 25/112025 | Not Started
2.1 | Research prediction algorithms | Algorithm selection report | ZAYED | 30/11/2025 | Not Started
2.2 | Build initial prediction model | Model v1.0 | ZAYED | 2025-01-12 | Not Started
2.3 | Train and optimize model | Trained model | HUSAM MOHAMED | 2025-01-12 | Not Started
3.1 | Test model accuracy | Test results | MOHAMMAD NASSAR | 2025-10-12 | Not Started
3.2 | Create prediction dashboard | Dashboard prototype | AMIR. SHAT | 15/12/2025 | Not Started
4.1 | Prepare final report | Project report | ZAYED | 17/12/2025 | Not Started
4.2 | Create presentation | Slides deck | HUSAM MOHAMED | 18/12/2025 | Not Started